## Summary Dashboard
TEST SUMMARY REPORT
Contact List API – Thinking Tester
Report Date: April 16, 2026 ¦ Prepared by: QA Team
| TOTAL TCs |  | PASSED |  | FAILED |  | PASS RATE | FAIL RATE
| 63 |  | 58 |  | 5 |  | 92.1% | 4.8%
PROJECT INFORMATION
| Project |  |  | Contact List API
| Base URL |  |  | https://thinking-tester-contact-list.herokuapp.com
| Test Cycle |  |  | Cycle 1
| Environment |  |  | Production (Heroku)
| Execution Date |  |  | April 16, 2026
| Tester |  |  | QA Team
| Tool |  |  | Postman / Manual
MODULE-WISE TEST RESULTS
| Endpoint | Module / Feature | Total TCs | Passed | Failed | Pass Rate | Priority
| POST /contacts | Add new Contact | 4 | 4 | 0 | 100.0% | High
| GET /contacts | Get Contact Info | 5 | 4 | 1 | 80.0% | High
| PUT /contacts | Replace Contact (Full Update) | 6 | 6 | 0 | 100.0% | Medium
| PATCH /contacts | Partial Update Contact | 4 | 3 | 1 | 75.0% | Medium
| DELETE /contacts | Delete Contact | 6 | 5 | 1 | 83.3% | Medium
| POST /users | Add New User | 6 | 6 | 0 | 100.0% | Medium
| GET /users/me | Get User Profile | 4 | 4 | 0 | 100.0% | High
| PATCH /users/me | Update User (Partial) | 8 | 6 | 2 | 75.0% | Medium
| POST /users/logout | Logout User | 7 | 7 | 0 | 100.0% | High
| POST /users/login | Login User | 6 | 6 | 0 | 100.0% | High
| DELETE /users/me | Delete User | 7 | 7 | 0 | 100.0% | High
| TOTAL |  | 63 | 58 | 5 | 92.1%

## Defect Log
DEFECT LOG
# | TC ID | Endpoint | Description | Expected | Actual | Severity | Priority | Status
1 | TC-CON-GET-005 | GET /contacts | GET request with non-existent contactId returns wrong status | 404 Not Found | 200 OK with full contact list returned | High | High | Open
2 | TC-CON-PATCH-004 | PATCH /contacts/:id | PATCH contact with empty JSON body returns 200 instead of 400 | 400 Bad Request | 200 OK – contact unchanged | Medium | Medium | Open
3 | TC-CON-DEL-003 | DELETE /contacts/:id | DELETE with very long fake ID returns 500 instead of 400 | 400 Bad Request | 500 Internal Server Error | High | High | Open
4 | TC-UR-PATCH-007 | PATCH /users/me | Sending integer as firstName accepted without validation error | 400 Bad Request – invalid data type | 200 OK – firstName stored as number | High | High | Open
5 | TC-UR-PATCH-008 | PATCH /users/me | Sending float as lastName accepted without validation error | 400 Bad Request – invalid data type | 200 OK – lastName stored as float | High | High | Open

## Test Cases Detail
DETAILED TEST CASES
TC ID | Description | Precondition | Auth | Method | Endpoint | Expected Result | Actual Result | Status
TC-CON-POST-001 | POST /contacts with all valid fields | User authenticated, {{token}} set | Bearer {{token}} | POST | /contacts | 201 Created + contact with _id | 201 Created as expected | Pass
TC-CON-POST-002 | POST /contacts with required fields only | User authenticated | Bearer {{token}} | POST | /contacts | 201 Created + _id, firstName, lastName | 201 Created as expected | Pass
TC-CON-POST-003 | POST /contacts without Authorization header | No auth header | No Auth | POST | /contacts | 401 Unauthorized | 401 Unauthorized | Pass
TC-CON-POST-004 | POST /contacts with malformed email | User authenticated | Bearer {{token}} | POST | /contacts | 400 Bad Request – email validation | 400 Bad Request | Pass
TC-CON-GET-001 | GET all contacts for authenticated user | At least 1 contact exists | Bearer {{token}} | GET | /contacts | 200 OK – array of contacts | 200 OK as expected | Pass
TC-CON-GET-002 | Verify TC-CON-001 contact appears in list | TC-CON-001 passed | Bearer {{token}} | GET | /contacts | 200 OK – John Doe present | 200 OK as expected | Pass
TC-CON-GET-003 | GET contacts without auth header | No auth | No Auth | GET | /contacts | 401 Unauthorized | 401 Unauthorized | Pass
TC-CON-GET-004 | GET specific contact by valid ID | {{contactId}} set | Bearer {{token}} | GET | /contacts/{{contactId}} | 200 OK – matching contact | 200 OK as expected | Pass
TC-CON-GET-005 | GET contact with non-existent ID | {{token}} set | Bearer {{token}} | GET | /contacts?{{contactId}}=000… | 404 Not Found | 200 OK – bug | Fail
TC-CON-PUT-001 | PUT full update of contact with valid data | Contact created | Bearer {{token}} | PUT | /contacts/{{contactId}} | 200 OK – updated contact | 200 OK as expected | Pass
TC-CON-PUT-002 | PUT missing required lastName field | Contact created | Bearer {{token}} | PUT | /contacts/{{contactId}} | 400 Bad Request | 400 Bad Request | Pass
TC-CON-PUT-003 | PUT with invalid auth token | Contact created | Bearer {{invalid_token}} | PUT | /contacts/{{contactId}} | 401 Unauthorized | 401 Unauthorized | Pass
TC-CON-PUT-004 | PUT with non-existent contact ID | fakeId set | Bearer {{token}} | PUT | /contacts/{{fakeid}} | 404 Not Found | 404 Not Found | Pass
TC-CON-PUT-005 | PUT with very long invalid contact ID | long fakeId set | Bearer {{token}} | PUT | /contacts/{{fakeid}} | 400 Bad Request | 400 Bad Request | Pass
TC-CON-PUT-006 | PUT with empty JSON body | Contact created | Bearer {{token}} | PUT | /contacts/{{contactId}} | 400 Bad Request | 400 Bad Request | Pass
TC-CON-PATCH-001 | PATCH update single field (firstName) | Contact created | Bearer {{token}} | PATCH | /contacts/{{contactId}} | 200 OK – firstName updated | 200 OK as expected | Pass
TC-CON-PATCH-002 | PATCH update multiple fields | Contact created | Bearer {{token}} | PATCH | /contacts/{{contactId}} | 200 OK – fields updated | 200 OK as expected | Pass
TC-CON-PATCH-003 | PATCH with invalid auth token | Contact created | Bearer {{invalid_token}} | PATCH | /contacts/{{contactId}} | 401 Unauthorized | 401 Unauthorized | Pass
TC-CON-PATCH-004 | PATCH with empty JSON body | Contact created | Bearer {{token}} | PATCH | /contacts/{{contactId}} | 400 Bad Request | 200 OK – bug | Fail
TC-CON-DEL-001 | DELETE existing contact | Contact created | Bearer {{token}} | DELETE | /contacts/{{contactId}} | 200 OK | 200 OK as expected | Pass
TC-CON-DEL-002 | DELETE non-existent contact | fakeId set | Bearer {{token}} | DELETE | /contacts/{{fakeid}} | 404 Not Found | 404 Not Found | Pass
TC-CON-DEL-003 | DELETE with very long invalid ID | long fakeId set | Bearer {{token}} | DELETE | /contacts/{{fakeid}} | 400 Bad Request | 500 Internal Server Error – bug | Fail
TC-CON-DEL-004 | DELETE already deleted contact | Contact deleted in pre-req | Bearer {{token}} | DELETE | /contacts/{{contactId}} | 404 Not Found | 404 Not Found | Pass
TC-CON-DEL-005 | DELETE with invalid auth token | Contact created | Bearer {{invalid_token}} | DELETE | /contacts/{{contactId}} | 401 Unauthorized | 401 Unauthorized | Pass
TC-CON-DEL-006 | DELETE after logout | User logged out | Bearer {token}} | DELETE | /contacts/{{contactId}} | 401 Unauthorized | 401 Unauthorized | Pass
TC-UR-POST-001 | Register new user with valid data | No existing email | None | POST | /users | 201 Created + user + token | 201 Created | Pass
TC-UR-POST-002 | Register with duplicate email | Email exists | None | POST | /users | 400 Bad Request | 400 Bad Request | Pass
TC-UR-POST-003 | Register missing password | — | None | POST | /users | 400 Bad Request | 400 Bad Request | Pass
TC-UR-POST-004 | Register with empty body | — | None | POST | /users | 400 Bad Request | 400 Bad Request | Pass
TC-UR-POST-005 | Register with invalid email format | — | None | POST | /users | 400 Bad Request | 400 Bad Request | Pass
TC-UR-POST-006 | Register with emoji in lastName | — | None | POST | /users | 201 Created | 201 Created | Pass
TC-UR-GET-001 | GET /users/me with valid token | User logged in | Valid Bearer Token | GET | /users/me | 200 OK + user info | 200 OK | Pass
TC-UR-GET-002 | GET /users/me with no auth | User exists | None | GET | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-UR-GET-003 | GET /users/me with invalid token | User exists | Invalid Bearer Token | GET | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-UR-GET-004 | GET /users/me with body included | User logged in | Valid Bearer Token | GET | /users/me | 200 OK (body ignored) | 200 OK | Pass
TC-UR-PATCH-001 | PATCH update firstName | User exists | Valid Bearer Token | PATCH | /users/me | 200 OK – updated | 200 OK | Pass
TC-UR-PATCH-002 | PATCH password too short (1 char) | User logged in | Valid Bearer Token | PATCH | /users/me | 400 Bad Request | 400 Bad Request | Pass
TC-UR-PATCH-003 | PATCH lastName exceeds 20 chars | User logged in | Valid Bearer Token | PATCH | /users/me | 400 Bad Request | 400 Bad Request | Pass
TC-UR-PATCH-004 | PATCH with empty body | User logged in | Valid Bearer Token | PATCH | /users/me | 400 Bad Request or 200 OK | 200 OK | Pass
TC-UR-PATCH-005 | PATCH with invalid field (age) | User logged in | Valid Bearer Token | PATCH | /users/me | 400 or 200 unchanged | 200 OK | Pass
TC-UR-PATCH-006 | PATCH with no auth token | User logged in | None | PATCH | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-UR-PATCH-007 | PATCH firstName with integer value | User logged in | Valid Bearer Token | PATCH | /users/me | 400 Bad Request | 200 OK – bug | Fail
TC-UR-PATCH-008 | PATCH lastName with float value | User logged in | Valid Bearer Token | PATCH | /users/me | 400 Bad Request | 200 OK – bug | Fail
TC-ULO-01 | Logout with valid token | User logged in | Bearer Valid | POST | /users/logout | 200 OK | 200 OK | Pass
TC-ULO-02 | Logout with empty token | — | Bearer Empty | POST | /users/logout | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULO-03 | Logout with invalid token | — | Bearer Invalid | POST | /users/logout | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULO-04 | Logout with expired token | Token expired | Bearer Old | POST | /users/logout | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULO-05 | Logout with very long token | — | Bearer Long | POST | /users/logout | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULO-06 | Logout with token having spaces | — | Bearer w/ spaces | POST | /users/logout | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULO-07 | Logout twice with same token | User logged in | Bearer used twice | POST | /users/logout | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULI-01 | Login with valid credentials | User registered | None | POST | /users/login | 200 OK + token | 200 OK | Pass
TC-ULI-02 | Login with incorrect password | User registered | None | POST | /users/login | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULI-03 | Login with unregistered email | — | None | POST | /users/login | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULI-04 | Login with empty email | — | None | POST | /users/login | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULI-05 | Login with empty password | — | None | POST | /users/login | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULI-06 | Login with missing fields | — | None | POST | /users/login | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULD-1 | Delete user with valid token | User logged in | Bearer Valid | DELETE | /users/me | 200 OK | 200 OK | Pass
TC-ULD-2 | Delete with empty token | — | Bearer Empty | DELETE | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULD-3 | Delete with invalid token | — | Bearer Invalid | DELETE | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULD-4 | Delete with expired token | Token expired | Bearer Old | DELETE | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULD-5 | Delete with very long token | — | Bearer Long | DELETE | /users/me | 401 / 400 | 401 Unauthorized | Pass
TC-ULD-6 | Delete with token having spaces | — | Bearer w/ spaces | DELETE | /users/me | 401 Unauthorized | 401 Unauthorized | Pass
TC-ULD-7 | Delete twice with same token | User deleted | Bearer used twice | DELETE | /users/me | 401 Unauthorized | 401 Unauthorized | Pass

## Metrics & Charts
TEST METRICS & CHARTS
Module | Pass | Fail
POST /contacts | 4 | 0
GET /contacts | 4 | 1
PUT /contacts | 6 | 0
PATCH /contacts | 3 | 1
DELETE /contacts | 5 | 1
POST /users | 6 | 0
GET /users/me | 4 | 0
PATCH /users/me | 6 | 2
POST /logout | 7 | 0
POST /login | 6 | 0
DELETE /users/me | 7 | 0
Result | Count
Pass | 58
Fail | 5